## Construction Labor
Botetourt Pilot Project Construction Labor
Job Code | Work Function Description | UOM | Unit Quantity | Price | Total | Definition
IFC-01 | Install Fiber Cable in Conduit | Per Cable Trench Ft. | 38758 | 0 | 0 | Includes: Installation of fiber cable in conduit with extra mule tape.
UG-01 | Trench 30" | Per Cable Trench Ft. | 0 | 0 | 0 | Includes: Trenching at 30" in depth and placement of 2" conduit in the trench (Contractor, please provide price only if trenching is available)
UG-02 | Directional Bore, 2" diameter Conduit | Per Cable Trench Ft. | 38673 | 0 | 0 | Includes: Set up and tear down of the bore rig. Placement of conduit at 30" depth or greater. Any depth less than 30" must be approved by Project Manager. Bore logs required every 50' (feet) with depth and distance from back of curb or edge of road asphalt/concrete. In areas where no reference can be made, Project Manager must be contacted. Bore log must match print addressing with street names and cross streets. Pictures of all conditions of bore area (before and after) must be taken and marked with address of location for managers use. All locates are to be called in. All state and city guidelines are to be followed. (NO SPOILS ALLOWED ON ANY GRASS OR DRIVEWAYS) Tarps or plywood are to be used. All boring and/or any excavation equipment must use plywood when entering or exiting private property at all times. All restoration of bore pits, potholes, and/or any area displaced must be restored to the original condition within 48 hours. All streets, sidewalks, and driveways must be cleaned within 24 hours of completion of bore shot. Any customer concerns and/or complaints must be turned over to Project Manager with addressing, contact phone number, and brief deception of concern. Contractor will be held liable for all driveways, streets, curbs, sidewalks, trees, stubs, flowers, mailboxes, and/or any private, state, and/or city property displaced from its original condition. Picture back up only will be used for disputing public concerns. All safety guidelines must be followed at all times. Proper control of work areas required. Men working signs must be used on sidewalks and streets. Traffic control, pedestrian control in and around work area must be supervised. Contractor to provide accurate as-builts.
UG-03 | Directional Bore Rock Adder for intermediate rock | Per Cable Trench Ft. | 10000 | 0 | 0 | Includes: This unit requires the use of specialized tooling (IE Trihawk, Rail-head, or Rockmaster) and for the bore shot to be attempted 3 times at varying depths to try to avoid the rock. If this code is used the city inspector must be on site to verify soil conditions. This code is paid by foot while in rocky conditions only.
UG-04 | Vault, HDPE up to 17"x30"x24" | Per Vault | 28 | 0 | 0 | Includes: All vaults will match surface level grade and contour of surface. All vaults must have a 4" base of Pea-Gravel. (Pea-Gravel will be purchased by contractor and invoiced back to customer with only a 3% mark-up. Contractor will buy in bulk, by the ton, stored at their site and hauled to job site in buckets or enclosed dumps to be distributed into vaults.) All vaults must set on top of base layer of pea gravel. Ant repellant must be applied to each vault location. (Small Vault and Medium Vault 1 bag and Large Vault 3 bags) . All vaults must have a ground rod installed at time of vault installation. All conduit will extend 2" above base layer or come in from the side no lower than 8 inches from bottom of base. All vaults will be placed with long vertical side lined up along sidewalk, curb, street and/or with direction of main conduit run. All covers, lids, and/or top mounting bolts must be installed to pass final inspection. NO vault will pass inspection if it has been cracked, split, or have broken edges and/or missing parts. Contractor to provide accurate as-builts.
UG-05 | Vault, HDPE up to 36"x48"x36" | Per Vault | 46 | 0 | 0 | See above
F-01 | Fusion splice optical fiber Loose Tube (Per fiber) | Per Splice | 551 | 0 | 0 | Includes: The preparatory work necessary to splice the fiber cables per specifications to include the installation of each enclosure. The fusion splicing and placement of the fibers in the splice enclosure. Installation of all splitters at each location if required and/or equipment is included when it is in the same enclosure. The sealing and storage placement of the enclosure to permanent installation. All underground splice enclosures will be mounted inside an underground vault on the side wall. Fiber post-splicing testing and documentation per specifications. All fibers are to be bonded and grounded per Customer specifications. Provide accurate as-builts. It is required that the contractor obtain, understand, and follow the closure manufacturer’s installation practice guidelines.
F-02 | Fiber Enclosure Installation | Per Enclosure | 9 | 0 | 0 | Includes: Installation of a new fiber cable enclosure for newly installed DF routes to include the preperation of any cables and express entries to be spliced or stored. The sealing and storage placement of the enclosure to permanent installation is also included in this line item. All cables are to be bonded and grounded per manufacturer specifications. Pictures required of final installation with naming sequence information from print. Required to provide accurate as-builts. Splicing is not included. It is required that the contractor obtain, understand, and follow the closure manufacturer’s installation practice guidelines.
TOTAL |  |  |  |  | 0
Alternate Items (Storm or Emergency Work. To be approved by Owner in advance.)
CW-06 | Emergency Call Out | Per Hour |  | 0 | 0 | Includes: Hour charges for after-hours work emergency. To be approved by Project Manager.
CW-07 | Trip Charge | Per Each |  | 0 | 0 | Includes: After-hours trip charge only to be used when hours are less than 4 hours. Approved by Project Manager.
ST-01 | Two Person Aerial Crew | Per Hour |  | 0 | 0 | Includes: Work to be performed by the hour. This includes bucket truck and all other equipment needed to perform Aerial work. Manager approval needed. Contractor to provide proper as-built.
ST-02 | Four Person Aerial Crew | Per Hour |  | 0 | 0 | Includes: Work to be performed by the hour. This includes bucket truck and all other equipment needed to perform Aerial Fiber work. Manager approval needed. Contractor to provide proper as-built.
ST-03 | Underground Crew | Per Hour |  | 0 | 0 | Includes: Work to be performed by the hour. This includes any equipment needed to perform Underground work. This crew must be a three man crew. Manager approval needed. Contractor to provide proper as-built.
ST-04 | Fiber Splicer | Per Hour |  | 0 | 0 | Includes: Work to be performed by the hour. This includes any equipment needed to perform Fiber testing or splicing with documentation work. Manager approval needed. Contractor to provide proper as-built.
ST-05 | Assessment Person | Per Hour |  | 0 | 0 | Includes: Work to be performed by the hour. This includes any equipment needed to perform work assessment of any job, work function, storm recovery or needs of the project manger. This person must be able to read maps, work with Excel & Word. Must be able to report findings in a concise and professional manner. Manager approval needed. Contractor to provide proper as-built.
ST-06 | Per diem | Per Crew |  | 0 | 0 | Includes: Emergency crew per diem charge for out of town addiction of labor during storm restoration. Approved only by Project Manager.
ST-07 | Emergency and /or Storm Rate per Hour | Per Crew |  | 0 | 0 | Includes: Emergency Crew hours(Crews must meet same required staffing and experience of normal crews working in system) during storm related restoration activity. Approved by Project Manager only.
ST-08 | Contract Construction Supervisor | Per Hour |  | 0 | 0 | Includes: Extra Crew Supervisor to only be used during Storm restoration activity. Approved by Project Manager only.
TOTAL |  |  |  |  | 0
Large Equipment
LQ-01 | Bucket Truck | Per Day (min) |  | 0 | 0
LQ-02 | Mini Excavator | Per Day (min) |  | 0 | 0
LQ-03 | Trencher | Per Day (min) |  | 0 | 0
LQ-04 | OTDR | Per Day (min) |  | 0 | 0
LQ-05 | Fusion Splice Machine | Per Day (min) |  | 0 | 0
LQ-06 | Trailer | Per Day (min) |  | 0 | 0
LQ-07 | 1 ton or bigger truck | Per Day (min) |  | 0 | 0
LQ-08 | Directional Drill | Per Day (min) |  | 0 | 0
LQ-09 | Locate Electronics | Per Day (min) |  | 0 | 0
LQ-10 | Rodder | Per Day (min) |  | 0 | 0
LQ-11 | Water Trailer | Per Day (min) |  | 0 | 0
LQ-12 | Cable Trailer | Per Day (min) |  | 0 | 0
LQ-13 | Splice Truck or Trailer | Per Day (min) |  | 0 | 0
TOTAL |  |  |  |  | 0

## Materials
Plan Name | Botetourt Pilot Project
Fiat | US Dollar
Material Type | Material Description | Part Number | Material Count | Material Rate | Material Rate Unit | Material Cost | Lead Time
Fiber 24ct | Fiber Cable, Singlemode, 024 ct, Single Armor, Single Jacket, Loose Tube, Zero Water Peak, Dry/Dry |  | 11985 | 0 | per foot | 0
Fiber 48ct | Fiber Cable, Singlemode, 048 ct, Single Armor, Single Jacket, Loose Tube, Zero Water Peak, Dry/Dry |  | 11401 | 0 | per foot | 0
Fiber 144ct | Fiber Cable, Singlemode, 144 ct, Single Armor, Single Jacket, Loose Tube, Zero Water Peak, Dry/Dry |  | 11773 | 0 | per foot | 0
Fiber 432ct | Fiber Cable, Singlemode, 432 ct, Single Armor, Single Jacket, Loose Tube, Zero Water Peak, Dry/Dry |  | 5568 | 0 | per foot | 0
Splice Closure | Dome Splice Closure, 24" x 10", 6 Round Ports, Includes 1 24f tray, B6 Size Basket, 3 Ground Feed-Through Lugs, Flash Valve, Tyco, FOSC450-B6-6-24-1-B3V |  | 9 | 0 | per unit | 0
Splice Closure | Splice Tray, 24Ct TE B Case |  | 24 | 0 | per unit | 0
Conduit | Conduit, HDPE, 2.00" SDR 11, Smooth Wall, Orange, No Tape, No Wire, 4000‘ Reel, Price per ft |  | 38673 | 0 | per foot | 0
Small Vault | Hand Hole Assembly, Polymer Concrete, 17" x 30" x 24", T15 Test Rated, Polymer Concrete, 1 Piece Cover, No Logo, Drop In, Hex Bolts |  | 28 | 0 | per unit | 0
Medium Vault | Hand Hole Assembly, Polymer Concrete, 30" x 48" x 36", 22500# Test Rated, Polymer Concrete, 1 Piece Cover, No Logo |  | 46 | 0 | per unit | 0
Large Vault | Hand Hole Assembly, Polymer Concrete, 36" x 72" x 36", 22500# Test Rated, Polymer Concrete, 1 Piece Cover, No Logo |  | 0 | 0 | per unit | 0
0

## Engineering
Phase | Task | UOM | Quantity | Unit Cost | Total Cost
Management | Project Management | Months | 3 | 0 | 0
Engineering | Construction Drawings | Foot | 38673 | 0 | 0
Engineering | Permit Package | Foot | 38673 | 0 | 0
Engineering | Traffic Control Plans | Foot | 38673 | 0 | 0
Engineering | Bill of Materials | Foot | 38673 | 0 | 0
Engineering | Splicing Schematics | Foot | 38673 | 0 | 0
Engineering | As-Built Posting | Foot | 38673 | 0 | 0
0